## Previous Lessons Learned
ID | Event/Category | Start/ Stop/ Continue | Action | Issue/Notes | Owner

## Key Decision Timeline
Task | Quarter | Month | Dependencies/Timing | 2023 Comments | Status | Owner
Identify Steering Committee Members | Q1 | 3
Identify Program Managers | Q1 | 3
Establish Key contact list for the campaign | Q1 | 3
Campaign Goals & Incentives - Recommendation | Q2 | 4
Campaign Goals & Incentives - Approval | Q2 | 5
Present Campaign Goals/Theme to United Way | Q2 | 5
Communicate dates to executive admins for calendars | Q1 | 3
Establish Campaign Theme | Q2 | 4
Share Theme, Goals and Incentives with leaders | Q3 | 8
Schedule meetings for Steering committee | Q2 | 5
Establish dates for key events | Q2 | 5
Notify United Way of dates | Q2 | 5
Campaign Goals & Incentives - Communicate goal to UW & Athene leaders | Q2 | 6
Identify Committee Leaders | Q2 | 6
Schedule Committee Meetings | Q2 | 6
Budget & Expense Orientation for Committees | Q2 | 6
Review prior year's lessons learned document | Q2 | 6
Committee Decisions - Organization | Q2 | 6
Form Committees | Q2 | 6
Order T-Shirts | Q2 | 6
Order Thank You Gifts | Q2 | 6
Invite Compliance to attend first prize committee meeting | Q3 | 7
Committee Decisions - Communication Deliverables | Q3 | 7
Communications to employees begin | Q3 | 7
Table Schedules - check with SteerCo members first to ensure availability | Q3 | 7
Committee Decisions - Event Name/Details | Q3 | 7
Budget Check-in | Q3 | 8
Committee Decisions - AV and Facilities Needs | Q3 | 8
Confirm that A/V and photographers have met regarding technical requirements and photo/video sizes | Q3 | 8
Make decisions on EWay messaging (customized or standard) | Q3 | 8
Determine who from United Way will be attending each day's events | Q3 | 8
Committee Decisions - Executive participation | Q3 | 8
Confirm all events are on Exec calendars as needed | Q3 | 8
Campaign Booklet Review & Approval | Q3 | 9
Provide schedule of events to United Way | Q3 | 9
Determine cutoff date for contributions through EWay | Q3 | 9
Remaining shirts to be put in storage | Q3 | 9
Determine date for Communications survey for feedback on campaign | Q3 | 9
Hold Lessons Learned meeting with committees | Q3 | 9
Hand out thank you gifts | Q4 | 10

## Committee Plan
Event Name
Committee Chair(s)
SteerCo Liaison
Event Date/Time
Featured Organization
Category | Deliverable | Owner | Due Date | Status | Notes
Milestone | Identify committee members
Milestone | Capture committee member shirt sizes
Milestone | Select featured organization
Milestone | Determine communication needs
Milestone | Determine event title and descriptions
Milestone | Determine prize/supplies needs and communicate
Milestone | Send final event title, description and initial communication needs
Milestone | Identify executive support for day
Milestone | Send event title, description
Milestone | Determine A/V and Facilities needs and communicate
Category | Deliverable | Owner | Due Date | Status | Notes